## Visit Summary
CRA SITE MONITORING REPORT
Generated: 2026-02-23 00:42:18 ¦ Clinical Data Management ¦ CONFIDENTIAL
I. Monitoring Metadata
CRA Name: | Study Lead
Site ID: | Site 1
Visit Date: | 2026-02-23 00:41:50
II. Data Quality Benchmarks
Total Patients |  | DQI Score |  | Clean Rate | Open Queries | SDV Completion
125 |  | 95.747 |  | 96.0% | 36 | 100%
III. Quality Metric Details
Metric Category | Current Performance | Protocol Target
SDV Completion | 5.5 | 100
Investigator Signatures | 98.8 | 100
Query Resolution Rate | 28 | 95
IV. Actionable Recommendations
Action Needed | Priority | Owner | Target Date
Complete SDV for 12 outstanding records | High | CRA | On-site
Resolve 12 open queries (aging > 14 days) | Medium | PI | 30-Apr-2026
Confirm AE coding for Patient 102 | Low | DM | 15-May-2026

## AI Analysis
AI-GENERATED PORTFOLIO ANALYSIS
Generated: 2026-02-23 00:42:18 ¦ Clinical Data Management ¦ CONFIDENTIAL
I. Executive Data Interpretation
The clinical portfolio comprises 125 patients across 1 investigative site. Current metrics indicate a high standard of data integrity, with a Data Quality Index (DQI) of 95.75% and a Clean-Patient Rate of 96.0%, both exceeding industry benchmarks of 90% and 80%, respectively. However, despite these strengths, the portfolio is currently 0% lock-ready due to a significant query backlog and unresolved administrative closures. The bottom-line verdict is that the portfolio is NOT lock-ready, posing a critical risk to regulatory submission timelines.
II. Key Findings
1. Data Quality Index (DQI): 95.75% — Surpasses the 90% threshold, indicating high initial data entry accuracy and effective site training.
2. Clean-Patient Rate: 96.0% — Exceeds the 80% industry benchmark, confirming that the majority of captured data has passed validation checks.
3. Query Density: 0.29 per patient — Significantly exceeds the 0.05 threshold, acting as the primary barrier to database lock and final analysis.
4. Database Lock Readiness: 0.0% — Fails to meet operational requirements for portfolio closure despite high data cleanliness, indicating administrative stagnation.
5. Safety Reporting: 0 SAEs reported for 125 patients — Indicates no immediate safety signals but necessitates CRA verification to rule out non-compliance with safety reporting SOPs.
6. Protocol Compliance: 0 deviations reported — Suggests high adherence to the study protocol or a potential gap in site-level identification and reporting of deviations.
7. Site Concentration: 100% of data from 1 site — Creates a single point of failure risk; any site-level compliance issue would impact the entire 125-patient dataset.
III. Portfolio Risk Analysis
Risk Area | Current Metric | Threshold | Gap | Impact | Highest Risk Studies
Query Backlog | 0.29 queries/patient | <= 0.05 | +0.24 | High | Portfolio-01
Data Completeness | 95.75% DQI | >= 90% | +5.75% | Low | Portfolio-01
Protocol Compliance | 0% Deviation Rate | <= 5% | 0% | Moderate | Portfolio-01
Patient Safety | 0 SAEs | N/A | 0 | Moderate | Portfolio-01
Clean-Patient Readiness | 96.0% | >= 80% | +16% | Low | Portfolio-01
KRI Coverage | 0% Lock Ready | 100% | 100% | Critical | Portfolio-01
IV. Strategic Recommendations
Area | Action Item | Owner | Priority | Target
Query Management | Execute site-level query resolution intensive to address 36 open queries. | CRA | Critical | Reduce open query rate to 0.05/patient within 14 days
Monitoring | Perform 100% Source Data Verification (SDV) on all 125 patient files to confirm zero SAE and deviation status. | CRA | High | Complete 100% SDV within 21 days
Data Management | Initiate Database Lock procedures for the 96% of patients currently marked as clean. | Data Manager | High | Transition 120 patients to lock-ready status within 7 days
Safety Review | Medical Monitor to perform a targeted review of adverse events to ensure no SAEs were misclassified. | Medical Monitor | Medium | Complete safety reconciliation report within 14 days
Site Training | Provide refresher training on Protocol Deviation identification and reporting procedures. | CRA | Medium | Document training for all site personnel within 15 days
Regulatory Affairs | Review data integrity metrics to prepare the clinical study report (CSR) shell based on 95.75% DQI. | Regulatory Affairs | Low | Draft CSR shell within 30 days
V. Conclusion
The portfolio demonstrates superior data quality and cleanliness metrics, but is currently stalled by a disproportionate query backlog that prevents database lock. To ensure regulatory success, the following targets must be met: • Target 1: Reduce open query rate to <= 0.05 queries/patient within 14 days • Target 2: Achieve 100% Database Lock Readiness within 21 days • Target 3: Complete 100% SDV of all 125 patients to verify zero SAE/Deviation reporting within 30 days